## Sheet1
| Objective | Date | Status
Obj1 | Validate satellite SST products to FRM standards. | 2019-09-01 | Data was obtained from EUMETSAT in 2019 and validation of satellite SST products to FRM standards is ongoing.
|  | 2021-01-01 | The validation of SST satellite data, including the SLSTR Sentinel-3 series, has shown that there is virtually no mean difference at night and only a small difference at daytime when compared with FRM data; this is a very good result. A paper on the validation is currently in final review and will be published this year (2021).
Obj2 | Maintain and evolve the International SST FRM Radiometer Network (ISFRN) and deploy on a continuous basis Thermal Infrared Radiometers (TIR) FRM and necessary supporting instrumentation to validate SST products. | 2019-05-01 | The instruments are all operated continuously and autonomously. Measurements are made continuously except in conditions of rain or excessive spray when the instrument shutters close automatically.
|  | 2020-04-01 | The operation of the instruments has been suspended due to the coronavirus pandemic. Operations will resume once it is safe to do so.
|  | 2020-04-16 | MS Norrona has resumed it's normal schedule (ISAR DMI resumes deployments).
|  | 2020-06-30 | Pont Aven has resumed it's ferry service (ISAR UoS resumes deployments).
|  | 2021-01-01 | The two ISAR (UoS and DMI) have been in near-continuous deployment since their ships of opportunity resumed their services early in the year, with a few disruptions caused by ongoing Covid-19 pandemic developments. The SISTeR deployments are expected to resume in June 2021.
|  | 2022-05-01 | All radiometers are now in continuous deployments again. SISTeR resumed its deployments on 20/03/2022
| Process, archive and quality control FRM4SST data following documented FRM procedures that approve their use for FRM satellite validation. | 2019-05-01 | Data is regularly uploaded to the Ifremer website.
|  | 2020-04-01 | Data upload and QC is still ongoing during the coronavirus pandemic, however may occur at a slower pace due to personnel having to work from home.
Obj3 |  | 2022-05-01 | Data upload and QC is still ongoing.
Obj4 | Deliver approved FRM4SST data sets and uncertainty budgets to users. | 2019-05-01 | Data is regularly uploaded to the Ifremer website and is available to download by registered users.
|  | 2020-04-01 | Data continues to be regularly uploaded to the Ifremer website and is available to download by registered users. However, there will be a gap in the data whilst the coronavirus pandemic halts ship deployments.
|  | 2022-05-01 | Data is regularly uploaded to the Ifremer website and is available to download by registered users.
Obj5 | Prepare and submit peer-reviewed journal articles. | 2019-05-01 | Ongoing
|  | 2020-01-01 | Two draft papers are under internal review.
|  | 2022-05-01 | One paper is ready to be submitted to a Journal. One draft paper has undergone internal review and updates. Another paper is being written for submission next year.
Obj6 | Conduct communications and outreach material promoting FRM4SST activity | 2019-05-01 | A twitter account has been created @ships4sst.org and the project news page is updated, roughly monthly.
|  | 2020-02-01 | Updates to the project news pages and internal discussions regarding outreach material are ongoing.
|  | 2022-05-01 | Updates to the project news pages and Twitter are ongoing, in particular with respect to the upcoming intercomparison exercise and workshop.